## Use Case Template
Project Title: Little Offices - Capstone Project Author/PM: Daniel Cender Release #: 0.4 5/20/23 Sprint #: 4
User Stories
ID | Feature | As a(n) <actor> | I would like to <description> | So that <outcome> | Estimate (hrs) | Assigned To | Delivery Status
F1 | Authentication | As a User | I would like to register and authenticate myself through a username/password pair | so that I can get a username and join a World | 2 | Myself | Completed
F2 | World Management | As a User | I would like to create a new World | so that I can access the game world | 2 | Myself | Completed
F3 |  | As a World Owner | I would like to secure my new World with a passcode | so I can protect access to my space/data | 1.5 | Myself | Completed
F4 |  | As a World Owner | I would like to delete one of my own Worlds | so I can clear out my stale data | 1.5 | Myself | Completed
F5 | World Selection | As a User | I would like to join one of my existing Worlds | so that I can load my saved whiteboard data | 1.5 | Myself | Completed
F6 |  | As a User | I would like to join another User's existing World | so that I can access the game world | 1.5 | Myself | Completed
F7 | Avatar Selection | As a User | I would like to select a premade pixel avatar before joining a World | so I can visualize my placement on the map | 2 | Myself | Cut From Scope
F8 | World Map | As a User | I would like to use my keyboard to move my avatar around the map | so I can navigate in relation to other features/Users | 3 | Myself | Cut From Scope
F9 | Text Chat | As a User | I would like to write and send messages to all other World Attendees | so that I can communicate visually | 4 | Myself | Completed
F10 | Voice Chat | As a User | I would like to broadcast voice data to other players in proximity | so that I can communicate verbally | 4 | Myself | Failed to Deliver on Time
F11 |  | As a User | I would like to hear other Users' voices when they're close | so that I can receive audible communication | 2 | Myself | Failed to Deliver on Time
F12 | World Whiteboard | As a User | I would like to interact with a whiteboard object in the map | so that I can enter the whiteboard edit view | 2 | Myself | Completed
F13 |  | As a User | I would like to edit the whiteboard with text/shape/paint tools | so that I can store persistent data on the World | 2 | Myself | Completed
F14 |  | As a User | I would like to see other Users' edits streamed to my browser | so that I can collaborate in realtime | 2 | Myself | Completed
F15 |  | As a User | I would like to export the World whiteboard as an image file | so that I can share my collaboration data | 2 | Myself | Completed
33