## Use Case Template
Project Title: Little Offices - Capstone Project Author/PM: Daniel Cender Release #: 0.4 5/20/23 Sprint #: 4
User Stories
ID | Feature | As a(n) <actor> | I would like to <description> | So that <outcome> | Estimate (hrs) | Assigned To | Delivery Status
NF1 | Security | As a User | My account and owned Worlds should be accessible only by myself | so that my data and identity is secure | 1.5 | Myself | Completed
NF2 |  | As a World Owner | I should be able to secure my created Worlds with a passcode | so only approved Users may enter the World | 1 | Myself | Completed
NF3 |  | As a World Owner | I would like deleting a World to clear all associated data (whiteboard state) | so I can fully manage my created data | 1 | Myself | Completed
NF4 | Availability | As a User | I would like to access the World map with below-avg WiFi and PC | so that I can fully utilize features without breaking immersion | 2 | Myself | Completed
NF5 |  | As a User | My World messages are reliably delivered to all connected browser clients | so that my communication is reliable | 1 | Myself | Completed
NF6 |  | As a User | I would like the World Map to function well even with many Users connected at once (4+) | so that my app experience isn't degraded | 2 | Myself | Completed
NF7 | Fault Handling | As a User | I would like the World map to gracefully close and redirect me when the Owner deletes it | so that I understand the cause of immediate app actions | 1 | Myself | Cut From Scope
9.5